# Crossing Points study team — check-in notes (raw)

SYNTHETIC DEMO FILE — all names, projects, and details are fictional and non-sensitive. For AI Workshops for DSPH, Workshop 3, Activity 1 Part A.

weds check-in, ~40 min. there: Jordan, Rosa, Mei, Tom. Priya out (conference).

corridor selection — cobbs creek pkwy is definitely in. second corridor still going back and forth between allegheny and lehigh, tabled AGAIN, need to just pick one

city data use agreement — sitting with OGC, rosa thinks the terms are fine but nobody has heard back in like 3 weeks. crash + signal timing data both depend on this

mei drafting the community intercept survey, wants it under 10 min. needs a spanish version too — who's doing that? nobody volunteered

IRB amendment for the intercept surveys — jordan checking with the irb office, hopefully back soon

budget — june community event went over on catering, need to watch the line. tom floated moving some funds from travel, we didn't land on anything

someone should book a room for the october community advisory board mtg before the calendar fills

side note — one of the student workers missed two shifts again, talked about coverage for the count sessions. keep this off anything shared

decided: monthly project newsletter starts september, rosa owns it

counter equipment — vendor quote came back ~15% over what we budgeted. revisit next meeting, or do we just go with the cheaper refurb units? tom to get one more quote maybe

next check-in two weeks, same time. mei sends survey draft before then

## Workshop prompt (copy into ChatGPT Edu)

“Turn these notes into three sections: (1) Summary in 3 bullets, (2) Decisions made, (3) Action items as a table with owner and due date. Flag anything that’s unclear or unassigned.”

## Then check

- Decisions: only ONE decision was actually made (the September newsletter). Did the AI invent others — the budget move, the equipment choice, the second corridor?

- Unassigned items: the Spanish translation and the October room booking have no owner. Did it flag them?

- Vague dates: “hopefully back soon” and “before then” — did it turn these into fake due dates?

- The student-worker note is a personnel matter. Should it be in a recap that goes to a shared Project everyone can see? (No — this is the shared-space test from the ethics segment.)